## Timeline
SENTINEL — Project Timeline
Generated: March 25, 2026 ¦ Start: March 25, 2026
Phase | Task | Owner | Priority | Status | Target Date | Notes
1 | Create Coinbase Developer Platform account | Nate | Critical | Not Started | 2026-03-25 | Need API keys for x402
1 | Create Alchemy account & get API key | Nate | Critical | Not Started | 2026-03-25 | Free tier sufficient for Phase 1
1 | Set up .env with real credentials | Nate | Critical | Not Started | 2026-03-26
1 | Integrate DeFiLlama hack/exploit API | Dev | High | Not Started | 2026-03-28 | Replace hardcoded exploit data
1 | Integrate Etherscan/Basescan contract verification | Dev | High | Not Started | 2026-03-30 | Contract age, verified source, proxy detection
1 | Wire up DeFiLlama TVL with protocol slug mapping | Dev | High | Not Started | 2026-03-30 | Currently passes null slug
1 | Test x402 payment flow end-to-end on Sepolia | Nate | Critical | Not Started | 2026-04-01 | Full cycle: 402 → pay → verify → response
1 | Deploy to persistent hosting (Railway/Cloudflare) | Dev | High | Not Started | 2026-04-04 | Need always-on endpoint for Bazaar
1 | Register on Bazaar with discovery metadata | Nate | High | Not Started | 2026-04-06 | Use Bazaar listing doc
1 | Publish Terms of Service | Nate | Medium | Done | 2026-03-25 | Drafted — needs legal review
1 | Write integration guide for agent builders | Dev | Medium | Not Started | 2026-04-08 | Code examples for AgentKit, ElizaOS
1 | Phase 1 launch — testnet live |  | Critical | Not Started | 2026-04-08 | MILESTONE
2 | Build /verify/position scoring engine | Dev | High | Not Started | 2026-04-15 | Liquidation, concentration, yield analysis
2 | Build /verify/token scoring engine | Dev | High | Not Started | 2026-04-19 | Honeypot, liquidity, holder concentration
2 | Add Redis caching layer (Upstash) | Dev | High | Not Started | 2026-04-22 | Target <200ms response times
2 | Implement free discovery tier (25 calls/wallet/day) | Dev | Medium | Not Started | 2026-04-24 | Critical for adoption
2 | Deploy to Base mainnet with real USDC | Nate | Critical | Not Started | 2026-04-29 | Switch network config + facilitator URL
2 | Publish as MCP server for Claude Desktop | Dev | Medium | Not Started | 2026-05-02 | Expands distribution
2 | Phase 2 launch — mainnet + 3 endpoints |  | Critical | Not Started | 2026-05-06 | MILESTONE
3 | Integrate OFAC SDN sanctions list | Dev | Critical | Not Started | 2026-05-14 | Zero tolerance — binary flag
3 | Build exploit address association graph | Dev | High | Not Started | 2026-05-21 | Tainted funds chain analysis
3 | Build transaction pattern behavioral scoring | Dev | High | Not Started | 2026-05-28 | Account age, volume, diversity
3 | Add ERC-8004 identity checking | Dev | Medium | Not Started | 2026-06-03 | As standard matures
3 | Phase 3 launch — counterparty intelligence |  | Critical | Not Started | 2026-06-08 | MILESTONE
4 | Build /preflight unified endpoint | Dev | Critical | Not Started | 2026-06-13 | Combines all verification domains
4 | Implement dynamic pricing (volatility-based) | Dev | Medium | Not Started | 2026-06-18 | 2-3x during stress events
4 | Add x402 V2 session token support | Dev | Medium | Not Started | 2026-06-23 | Bulk discount for high-frequency agents
4 | Expand to Arbitrum + Optimism | Dev | Medium | Not Started | 2026-07-03 | Multi-chain support
4 | Explore B2B white-label partnerships | Nate | Low | Not Started | 2026-07-13 | Agent platforms, institutional DeFi
4 | Phase 4 launch — full trust oracle |  | Critical | Not Started | 2026-07-23 | MILESTONE
Total Tasks |  |  | 30

## Milestones
SENTINEL — Key Milestones
Milestone | Target Date | Phase | Success Criteria
Phase 1: Testnet Live | 2026-04-08 | 1 | /verify/protocol working on Sepolia, discoverable in Bazaar, payment flow tested
Phase 2: Mainnet + 3 Endpoints | 2026-05-06 | 2 | Real USDC payments, /verify/position + /verify/token live, <200ms responses
Phase 3: Counterparty Intelligence | 2026-06-08 | 3 | Sanctions screening, exploit association, behavioral scoring operational
Phase 4: Full Trust Oracle | 2026-07-23 | 4 | /preflight endpoint live, dynamic pricing, session tokens, multi-chain
First 1,000 paid calls | 2026-05-24 | 2 | Revenue validation — agents are discovering and paying for verification
First $1,000 monthly revenue | 2026-06-23 | 3 | Business viability confirmed at moderate scenario trajectory

## Costs
SENTINEL — Cost Structure
Category | Phase 1 (Monthly) | At Scale (Monthly) | Notes | Status
Hosting (Railway/CF Workers) | 0 | 50 | Free tier → paid at scale | Free tier
RPC/Data (Alchemy) | 0 | 125 | Free tier = 300M compute units/mo | Free tier
DeFiLlama API | 0 | 0 | Free, no API key required | Free
Cache (Upstash Redis) | 0 | 20 | Free tier = 10K commands/day | Phase 2
Domain + SSL | 1 | 1 | $12/yr | Needed
x402 Facilitator Fee | 0 | 750 | 5% of revenue | Auto
TOTAL | 1 | 946